## Overall Package, System Intg.
Engineering Product Development Cycle | % | Fullfillment plan / resource
Specs | 5% | See High Level Specification Document·and Specs in the Integration PDR
Research / Development | 5% | 4WD Concept Evaluation and Integration PDR
Design / CAD | 10% | Full Vehcile Assemblies / Renders. Integrated model of lower level subsystem assemblies
Data Collection for Analysis | 15% | - last years endurance data, suspension obstacle data (LVDT), turning rate data - Tire data, pad data, engine dyno data - 2021 midnight mayhem data - Competition point analysis
Analysis / Calculations / CAE | 20% | 1 - Integration PDR and ADAMS model simulations for maneuverability: slalom, steady state turn radius, transient turn radius 2- ADAMS Drop Model
Testing / Validation | 20% | 1 - Collect manuverability / traction / diff output data. Would need to quanitfy wheel slip, wheel angles, wheel speed, and turning radius / yaw for various manuvers and common terrain (dry dirt, mud, asphalt, grassy) 2 - Validation of load cases (full suite of accels, IMUS, Transducers/Strain Gauges) during worst loading conditions
Correlation of Analysis and Testing | 20% | 1 - Qualify diff selection, establish limits on acceptable slip / wind up, prove vehcile meets high level manuv specs and speed specs. 2 - Compare load cases to simulink loads and refine model.
Other | 5% | Potential to include dynamic model and its own validation path here
Score | 35

## Suspension, Steering, Brakes
| Engineering Product Development Cycle | % | Fullfillment plan / resource
Suspension | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | PDR documents, Suspension Parameter Research
| Design / CAD | 10% | 1 - Component Design 2 - MATLAB Optimization for Kinematic Points
| Data Collection for Analysis | 15% | 1 - Fox dyno data, our dyno data 2 - 2020 Obsticle data (LVDT)
| Analysis / Calculations / CAE | 20% | 1 - Damping model for tuning shim stacks 2 - FEA 3 - ADAMS model maneuverability simulations
| Testing / Validation | 20% | 1 - Whoop traversal with varing shim stacks. Collect LVDT data on shocks and pitching moment with IMUs 2 - FEA model validation with destructive testing on steering / camber links with transducer/strain gauges attached
| Correlation of Analysis and Testing | 20% | 1 - Compare shock whoop response to damping model or even simscape analysis (tie back to obsticle traversal specs) 2 - Compare data to load case specs, improve FEA models 3 - Compare physical testing to ADAMs simulation
| Other | 5% | Bonus load case / FEA model validation
| Score | 12
Steering | Specs | 5% | See spec document
| Research / Development | 5% | Cockpit control forces, column and rack PDR, steering geometry research
| Design / CAD | 10% | Component Design
| Data Collection for Analysis | 15% | -Antiroll bar / turning radius data collected in 2020 -Manuverability course data collected over years (documented in high level specs)
| Analysis / Calculations / CAE | 20% | 1 - Ackerman change captured in kinematic optimization 2 - Model for over/understeer gradient (would predict our min transient turning radius - may need to tie in diff / wheel slip info), longer term would be ADAMS vehicle dynamic model 3 - FEA
| Testing / Validation | 20% | 1 - Measure actual car ackerman change during transiet maneuvers combined with wheel slip and vehcile turn radius (potenitally adjust / change ackerman during transient manuvers). Correlate to windup as well. 2 - Measure yaw / slip angles to quanitfy oversteer gradient
| Correlation of Analysis and Testing | 20% | 1 - Compare actual ackerman to designed and to target in diff selection analysis. Identify acceptable ackerman range for manuv performance and windup. 2 - Correlate yaw / slip angles to oversteer gradient model to inform antiroll bar design and roll center height selection.
| Other | 5% | Steering link FEA model validation with distructive testing
| Score | 12
Brakes | Specs | 5% | High level specs and subsystem specs
| Research / Development | 5% | PDRs
| Design / CAD | 10% | Component design
| Data Collection for Analysis | 15% | - 2020 tire friction coeff data - 2020 rotor friction coeff data - 2020 brake line pressure data
| Analysis / Calculations / CAE | 20% | 1 - Analytical braking model 2 - FEA 3 - Rotor thermal analysis
| Testing / Validation | 20% | 1 - Data collection on all braking model parameters: Driver input force, line pressure, caliper output force, refine rotor friction coeff data, refine tire friction coeff data 2 - FEA model validation with a focus on pedal weight reduction 3 - Rotor FEA / Thermal model validation - collecting temperture data from rotors during mock race
| Correlation of Analysis and Testing | 20% | 1 - Compare real brake model parameters to estimated and update. Compare braking performance in model to actual cars 2 - Refine FEA model and component load cases 3 - Refine rotor thermal model
| Other | 5%
| Score | 12

## CVT, Reduction Box, Hubs, Axles
| Engineering Product Development Cycle | % | Fullfillment Plan / Reference Document
CVT / Transmission | Specs | 5% | Subsystem spec document and high level specs
| Research / Development | 5% | CVT PDR, tuning guide, other CVT reports
| Design / CAD | 10% | Modified stock components
| Data Collection for Analysis | 15% | 2020 primary and secondary data
| Analysis / Calculations / CAE | 20% | Analytical model of cvt for tuning (weight selections, ramp angles, springs, etc.)
| Testing / Validation | 20% | Test out suite of components derived from analytical model and compare to ideal shift curve (will require primary and secondary rpm sensing). Targeting accel times in specs
| Correlation of Analysis and Testing | 20% | Compare actual performance to that predicted by model. Refine model.
| Other | 5% | Establish CVT efficiency
| Score | 10-15
Reduction Box, Hubs, and Axles | Specs | 5% | High level specs
| Research / Development | 5% | PDRs and high level design document
| Design / CAD | 10% | Component Design
| Data Collection for Analysis | 15% | -2020 engine dyno data -2020 endurance data
| Analysis / Calculations / CAE | 20% | 1 - Simulink accel model 2 - FEA
| Testing / Validation | 20% | 1 - Validating simscape model accel and maybe hill climb performance. Measure actual input parameters and their effects on performance. 2 - Driveshaft failure testing to validate loadcases. 3 - Driveshaft windup / torsional rigidity testing to determine acceptable criteria
| Correlation of Analysis and Testing | 20% | 1 - Compare actual performance to theoretial and to spcs. Refine simscape model and ratio selection for future years. 2 - Refine FEA models and drivetrain loadcases
| Other | 5%
| Score | 20-25

## Chassis, Ergo
| Engineering Product Development Cycle | % | Fullfillment Plan / Reference Document
Chassis | Specs | 5% | High level specs / subsystem specs
| Research / Development | 5% | PDRs and Nose Design research
| Design / CAD | 10% | Frame / Mount design / body panels
| Data Collection for Analysis | 15% | 1 - 2020 torsional stiffness testing and frame weight 2 - Drag coefficient of 2020 car
| Analysis / Calculations / CAE | 20% | 1 - Torsional stiffness FEA 2 - Drag model (CFD), quantify drag reduction. Relate to nose design change and body panels
| Testing / Validation | 20% | 1 -Torsional stiffness test. No clue about tieing in manuv 2 - Aero / Wind tunnel testing for drag reduction, combine with full scale accel testing (with various total car weight, [this will also help refine simscape model])
| Correlation of Analysis and Testing | 20% | 1 - Justify the change to nose design with torsional acceptable torsional stiffness values 2 - Compare model, to windtunnel, to full scale. Refine model. Compare full scale to specs. Justify increased body panel weight and increased gusset weight
| Other | 5%
| Score | 25
Ergo | Specs | 5% | High level specs
| Research / Development | 5% | Seat PDR / Driver model research / Vibration Research
| Design / CAD | 10% | Component design
| Data Collection for Analysis | 15% | -Do a 2020 car driver survey -Bruising -Measure drivers bodies (this could be done remotely) -Engine Frequency and Amplitude of Vibration, Road frequency and amplitude of vibrations
| Analysis / Calculations / CAE | 20% | 1 - Seat / Wheel heat map model? 2 - Driver model 3 - Seat / wheel FEA 4 - Engine Damping
| Testing / Validation | 20% | 1 - Seat / Wheel thermal imaging 2 - Driver model full investigation combine with ergo rig 3 - Destructive testing of components 4 - Testing vibration using accelerometers
| Correlation of Analysis and Testing | 20% | -Compare test to model. Can interate on wheel in one cycle easily. Seat not so much -Correlate vibration test results with model
| Other | 5%
| Score | 20-25