## Overall Package, System Intg.
Engineering Product Development Cycle | % | Fullfillment plan / resource
Specs | 5% | 1. High Level Spec Document -Competition Points Analysis 2. Integration PDR Specs for 4WD
Research / Development | 5% | 1. VIP Concept Evaluation 2. Integration PDR Concept Evaluation 3. Research into load cases from past experience
Design / CAD | 10% | Full Vehcile Assemblies / Renders. Assemblies reflect subsystem integration ie toebox assembly, rear assembly, cockpit assembly
Data Collection for Analysis | 15% | 1. ADAMs diff layout sim: vehicle weight, COM, suspension geometry, tire COF, engine curve, CVT curve, spring and ARB rates and damping -show where we initially got this data, Weight Budget, perfect kinematics, tire tests last year, ideal CVT curve 2. Static Structural Load Cases: LDS data (motion of shocks), strain guage data (stress on links), chassis and suspension geometry
Analysis / Calculations / CAE | 20% | 1. ADAMs diff layout Sim: step steer turn radius (5, 10, 15 mph), slalom, maneuverability track -Use Integration PDR as analytical validation of the complex model -DOE varying parameters: Ackerman Curve (1), front spring rates (3), front damping rates (?), rear spring rates (3), rear damping rates (?), ARB rate (5), driveshaft (2-3), diff mode (3). Experiments: step steer turn radius (5, 10, 15 mph), slalom, maneuverability track -compliant driveshaft wasn't included in ADAMS model, our safest drive shaft will serve as control, design for super high stiffness 2. Static Structural Load Cases -ADAMs drop model to get wheel forces
Testing / Validation | 20% | 1 - Collect manuverability / traction / diff output data. Would need to quanitfy wheel slip, wheel angles, wheel speed, and turning radius / yaw for various manuvers and common terrain (dry dirt, mud, asphalt, grassy) 2 - Validation of load cases (full suite of accels, IMUS, Transducers/Strain Gauges) during worst loading conditions
Correlation of Analysis and Testing | 20% | 1. ADAMs diff layout Sim: take measurements on all input parameters, replicate the simulations in real life, update input parameters in the model and compare model results to real life results -turn radius with 2WD, open 4WD, locked 4WD (maybe add in ARB to this experiment) -relative manuv track times -slalom or any other obstacle 2. Load Cases: take measurements on suspension and chassis geometry, replicate the load cases (drop, log, turn, add any other obstacles we test), update input parameters into the model and compare model stress results with measured stress results in links
Other | 5% | Manufacturing and Serviceability: body panel design?, toebox layout?, driveshaft serviceability?
Score | 35

## Suspension, Steering, Brakes
| Engineering Product Development Cycle | % | Fullfillment plan / resource
Suspension | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | PDR documents, Suspension Parameter Research
| Design / CAD | 10% | 1. Front Suspension Assembly: must have all hardware 2. Rear Suspension Assembly: must have all hardware
| Data Collection for Analysis | 15% | 1. MATLAB Kinematics: Faro Scanner 2. ADAMs shock and ARB DOE: Fox and in-house dyno (spring and damping rates), ARB rates, 2020 LDS obstacle data? 3. ARB math model: extender lengths, tube material properties, link geometry 4. Component FEA: material properties, loading, boundary conditions
| Analysis / Calculations / CAE | 20% | 1. MATLAB Kinematics 2. ADAMs shock and ARB DOE -damping model for shim stacks 3. ARB Math model 4. Component FEA
| Testing / Validation | 20% | 1. MATLAB Kinematics: Measure the camber and toe curve on the car statically by moving the suspension through full travel fully unloaded 2. ADAMs shock and ARB DOE: run spring rate, damping rate, ARB rate DOE for lap time, whoop traversal -shock dyno to determine accuracy of damping model for shim stacks 3. ARB Math Model: TST for the ARB? 4. Component FEA: strain guages on links to give actual stress, extrapolate to update loading conditions on a-arms, trailing arm
| Correlation of Analysis and Testing | 20% | 1. MATLAB Kinematics: input measured suspension geometry into GUI, compare parameters of interested with our measured parameters 2. ADAMs shock and ARB DOE: input measured suspension geometry and spring and damping rates, compare whoop traversal pitching, LDS data, etc. 3. ARB Math Model: compare torsional stiffness test results with model results after updating geometry and material property parameters 4. Component FEA: Compare FEA results to strain guage data after updating suspension geometry and material properties in FEA model
| Other | 5% | Manufacturing/Serviceability: 3D printed upright, a-arm donuts/bearing selection, hexagon link inserts
| Score | 12
Steering | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | Cockpit control forces, column and rack PDR, steering geometry research
| Design / CAD | 10% | 1. Steering Column Assembly 2. Front Suspension Assembly -combine all this into one assembly
| Data Collection for Analysis | 15% | 1. MATLAB Kinematics: Faro scan suspension geometry 2. ADAMs Ackerman % Sim: 2020 anti roll bar stiffness -this one is kinda tough because ackerman %, suspension geometry, shock and arb (k,c), and diff layout contribute to turn radius and manuv 3. Component FEA: suspension geometry, loads, constraints -Antiroll bar / turning radius data collected in 2020 -Manuverability course data collected over years (documented in high level specs)
| Analysis / Calculations / CAE | 20% | 1. MATLAB Kinematics 2. ADAMs Ackerman % Sim 3. Component FEA 1 - Ackerman change captured in kinematic optimization 2 - Model for over/understeer gradient (would predict our min transient turning radius - may need to tie in diff / wheel slip info), longer term would be ADAMS vehicle dynamic model 3 - FEA
| Testing / Validation | 20% | 1. MATLAB Kinematics: measure ackerman change (tape or something better) 2. ADAMs Ackerman % Sim: measure turn radius to replicate step steer 3. Component FEA: stress on steering links from strain guages 1 - Measure actual car ackerman change during transiet maneuvers combined with wheel slip and vehcile turn radius (potenitally adjust / change ackerman during transient manuvers). Correlate to windup as well. 2 - Measure yaw / slip angles to quanitfy oversteer gradient
| Correlation of Analysis and Testing | 20% | 1. MATLAB Kinematics: how does our measured ackerman compare to the what the model outputs after updating parameters? 2. ADAMs Ackerman % Sim: compare turn radius after updating ADAMs parameters 3. Component FEA: compare stress in links to strain guage data after updating geometry
| Other | 5% | Manufacturing and Serviceability: custom rack? U-joint drive shaft to get around diff
| Score | 12
Brakes | Specs | 5% | High level specs and subsystem specs
| Research / Development | 5% | PDRs
| Design / CAD | 10% | Full subsystem CAD with hardware and brake line routing
| Data Collection for Analysis | 15% | 1. Analytical Braking Model: tire COF, caliper-rotor COF, radius tire, radius rotor, car weight, brake line pressure - tire COF: static and dynamic tire COF test rig - caliper-rotor COF: run static test again - brake line pressure: get from pressure sensor - brake pedal angle 2. Brake Pedal FEA and Generative Design: input load, constraints, material properties - material properties come from GE - input loads come from brake line pressure. 3. Rotor Thermal Model: what are the input parameters for the model?
| Analysis / Calculations / CAE | 20% | 1. Analytical braking model 2. Brake Pedal FEA and Generative Design 3. Rotor thermal model
| Testing / Validation | 20% | 1. Analytical Braking Model: torque arm with load cell fixed to the chassis on the rear axle and each of the front axles. 2. Brake Pedal FEA and Generative Design: Destructive testing on the break pedal. Ideally we would measure the stress distribution throughout the pedal. Experiment requires a test rig. Maybe a high speed camera could be used. 3. Rotor thermal model: Measure temperature distribution on rotor. T(radius, time). See if it's possible to collect real time temp data during testing.
| Correlation of Analysis and Testing | 20% | 1. Analytical Braking Model: Input new parameters into model to output the torque requirement to lock the wheels, compare model results to experimental torque results. 2. Brake Pedal FEA: Input new loading conditions derived from brake line pressure to get new input force and get new stress distribution from model. Compare model results to test rig results. Compare the critical force to break the pedal from the model with that from the test rig. 3. Rotor Thermal Model: Compare temp distribution of thermal model to experimentally determined temp distribution.
| Other | 5% | Manufacturability and Serviceability: 3D Printing, toebox packaging,
| Score | 12

## CVT, Reduction Box, Hubs, Axles
| Engineering Product Development Cycle | % | Fullfillment Plan / Reference Document
CVT / Transmission | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | CVT PDR, tuning guide, other CVT reports, 2020 eCVT experience
| Design / CAD | 10% | Full Assembly displaying modified components vs stock components
| Data Collection for Analysis | 15% | 1. Parameters for CVT model: flyweights, ramp angles, spring stiffnesses…
| Analysis / Calculations / CAE | 20% | 1. Analytical model of cvt for tuning
| Testing / Validation | 20% | 1. On car testing: monitor primary RPM to hold it at the RPM where the engine produces maximum power. Do we want to hold the engine at the RPM with max torque. Create RPM vs Ratio plot (engagement RPM, straight shift RPM, upshift RPM, backshifting RPM). 2. Dyno testing: RPM vs Ratio plot. Torque vs RPM plot. Means we need to know the CVT ratio, can get from divding secondary RPM by primary RPM or directly measuring sheave distance. 3. Experiment to tune parameters for each event: accel, hill climb, sled pull, and after that manuv and endurance. 4. Experiment to determine if keeping engine RPM at max HP or max torque is the best. Accel runs, manuv runs, hill climb runs.
| Correlation of Analysis and Testing | 20% | 1. Update model parameters with those used during testing and compare model results with experimental results.
| Other | 5% | Manufacturing and Serviceability: components we manufacture ourselves
| Score | 10-15
Reduction Box, Hubs, and Axles | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | PDRs, drivetrain research papers, machinery's handbook, shigleys, dudley's
| Design / CAD | 10% | 1. Full Drivetrain Assembly 2. Exploded view of gearbox 3. Hub Assembly 4. Scanned Diff lol
| Data Collection for Analysis | 15% | 1. Simulink Drivetrain Model: Engine curve, CVT curve, rolling resistance, drag coefficient, vehicle CG, vehicle weight, check model again 2. Gear Design Spreadsheet and Powergear: loading conditions ie torque vs time. We can get this from secondary and primary RPM data by calculating a CVT ratio and using dyno data to get torque. 3. Hub FEA and Generative Design: loads 4. Matlab code for shaft design: loading conditions -statically break drive shaft material and measure max shear stress/critical torque load. multiple trials 5. Excel spreadsheet for spline design: loading conditions
| Analysis / Calculations / CAE | 20% | 1. Simulink Drivetrain Model 2. Gear Design Spreadsheet and Powergear 3. Hub FEA and Generative Design 4. Matlab code for shaft design 5. Excel spreadsheet for spline design
| Testing / Validation | 20% | 1. Simulink Drivetrain Model: Run accel and hill climb experiments and get times 2. Gear Design Spreadsheet and Powergear: Dye penetration on gears and examine micro cracks under a microscope, crack propagation techniques backout fatigue life 3. Hubs FEA and Gen Design: measure stress in hubs 4. Matlab code for shaft design: backout loads from primary and secondary RPM -Design a driveshaft with a SF of 1 for our max torque load case and test to failure on endurance course, recording life time to back out fatigue loading 5. Excel spreadsheet for spline design: backout loads from primary and secondary RPM
| Correlation of Analysis and Testing | 20% | 1. Simulink Drivetrain Model: update simscape parameters and compare accel and hill climb times with experimental results 2. Gear Design Spreadsheet and Powergear: Convert microcrack size to fatigue life and compare with Powergear model 3. Matlab code for shaft design: compare load cases from design with experimentally derived loads 4. Excel spreadsheet for spline design: compare load cases from design with experimentally derived loads
| Other | 5% | Manufacturing and Serviceability: process for assembly and disassembly, CNC work on TC, gears, 3D printed hubs
| Score | 20-25

## Chassis, Ergo
| Engineering Product Development Cycle | % | Fullfillment Plan / Reference Document
Chassis | Specs | 5% | High Level Specifications and Sub-system Level Specifications
| Research / Development | 5% | PDRs, Nose Design decision matrix, CFD/Aero Research
| Design / CAD | 10% | 1. Frame with all mounts and tabs 2. Separate exploded view of each subsystem mounting to chassis. Shoe suspension, drivetrain, driver controls, panels
| Data Collection for Analysis | 15% | 1. Structural FEA: loading conditions, material properties (from VR3), boundary conditions, chassis geometry - loading conditions: LDS sensors - material properties: VR3 - chassis boundary conditions: figure it out - Faro scan chassis? 2. Torsional Stiffness FEA: chassis geometry and material properties 3. CFD Drag Model: chassis geometry, panel geometry, air density, vehicle velocity, suspension and wheel geometry
| Analysis / Calculations / CAE | 20% | 1. Structural FEA 2. Torsional stiffness FEA 3. CFD Drag Model
| Testing / Validation | 20% | 1. Structural FEA: can't think of a way to directly measure the stress distribution 2. Torsional stiffness FEA: increasingly load the chassis with a twisting moment and measure angle of deflection. Result in an average torsional stiffness value 3. CFD Drag Model: Experimentally determine the drag coefficient of the vehicle. Figure out what this experiment is going to look like (3d printed scale model, full wind tunnel testing?)
| Correlation of Analysis and Testing | 20% | 1. Structural FEA: Ideally compare model stress results to experimentally measured stress results. 2. Torsional stiffness FEA: compare torsional stiffness value of model to experimentally determined value 3. CFD Drag Model: update model parameters and find new drag coefficient, compare to experimentally measured drag coefficient
| Other | 5% | Manufacturing and Serviceability: Chassis welding jig, composite fabrication process, body panel design for serviceability, 3D printed a-arm mount jigs
| Score | 25
Ergo | Specs | 5% | High level specs
| Research / Development | 5% | Seat PDR / Driver model research / Vibration Research
| Design / CAD | 10% | Driver Cockpit Assembly: chassis, driver assembly, seat, foot plate, pedals, steering column and wheel, belts, firewall, kill switch SIM, extinguisher, literally everything the driver interacts with
| Data Collection for Analysis | 15% | -Do a 2020 car driver survey -Bruising -Measure drivers bodies (this could be done remotely) -Engine Frequency and Amplitude of Vibration, Road frequency and amplitude of vibrations
| Analysis / Calculations / CAE | 20% | 1. RAMSIS Ergo Software or something similar
| Testing / Validation | 20% | 1. Driver Surveys
| Correlation of Analysis and Testing | 20% | 1. Correlate survey results with model results
| Other | 5% | Manufacturing and Serviceability: composite procedure, custom foam seat cushions
| Score | 20-25