## Daily Schedule
Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42 | [6 empty] | Week 43 | [6 empty] | Week 44 | [6 empty] | Week 45 | [6 empty] | Week 46 | [6 empty] | Week 47 | [6 empty] | Week 48 | [6 empty] | Week 49 | [6 empty] | Week 50 | [6 empty] | Week 51 | [6 empty] | Week 52 | [6 empty] | Week 53 | [6 empty] | Week 54 | [6 empty] | Week 55 | [6 empty] | Week 56
Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
 | time axis 2019-12-15 to 2020-06-20
ANSYS Torsional Stiffness Model
Torsional Stiffness Rig Design Changes | [20 empty] | Build / Modify Torsional Stiffness Rig | [9 empty] | Test
Driver Survey of Last Year's Seat
[21 empty] | Seat Composites Work | [21 empty] | New Seat Driver Survey
[14 empty] | Shim Design and Review | [7 empty] | Waterjet Shim Stacks | [5 empty] | Run Shock Dyno
ADAMS Ride Analysis
Build Whoops (Justin) | [47 empty] | Obstacle Testing
Ramp Design (Jacob) | [23 empty] | Build Ramp
Slip Angle Measurement Mounting Hardware Design | [21 empty] | Slip Angle Measurement Hardware Manufacturing | [18 empty] | Check | [6 empty] | Test | [13 empty] | Test
ADAMS Oversteer Model
[21 empty] | DAQ Preparation for Slip Angle / Oversteer Tests | [26 empty] | Test | [13 empty] | Test
[21 empty] | Build Rig for Pad Coefficient (Nachuan) and Tire Coefficient (Gian) | [7 empty] | Run Tests
Braking Math Model Corrections
[21 empty] | DAQ Preparation for Brake Line Pressure Logging | [26 empty] | Test | [13 empty] | Test | [20 empty] | Test
[21 empty] | Dyno 2019 Engine | [7 empty] | Dyno 2020 Engine
Simulink Acceleration Model w/ Controller
Stopwatch Testing for Acceleration & Maneuverability
DAQ Preparation for RPM Logging
Refine Pitting Estimation
Die Penetrant Test & Microscope Imaging
[49 empty] | Redesign & Repair (as necessary) | [13 empty] | Redesign & Repair (as necessary) | [20 empty] | Redesign & Repair (as necessary) - Requires Additional Test Day | [19 empty] | Last Chance Test
[42 empty] | Rough Formatting of Posters & Flow of Oral Presentations | [14 empty] | Rough Draft & Resource Gathering for Poster & Oral Presentation | [26 empty] | Final Draft | [14 empty] | Internal Review | [6 empty] | External Review | [6 empty] | Revisions & Polish | [16 empty] | Review Presentation Feedback | [5 empty] | Edit & Polish | [19 empty] | Review Feedback |  |  | Edit & Polish | [16 empty] | Review Feedback |  |  | Determine New Design Goals for 2021
[114 empty] | Pack | [6 empty] | 25 hr drive |  | ARIZONA |  |  |  | Return Drive | [16 empty] | Pack | [5 empty] | 6 hr | LOUISVILLE | [13 empty] | Pack |  |  |  |  | 10 hr | ILLINOIS

## Weekly Schedule
|  | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
|  | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 | 2020-04-05 | 2020-04-12 | 2020-04-19 | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17 | 2020-05-24 | 2020-05-31 | 2020-06-07
Special Classification |  | 2020-01-26: TEST DAY; 2020-02-09: TEST DAY; 2020-03-01: TEST DAY
[9 empty] | 2019-02-01 |  | 2019-02-15 |  |  | 2019-03-07
Chassis
Data Collection
ANSYS stiffness test | bar: 2019-12-08 to 2020-01-05
| Torsional stiffness test | 2019-12-08: Design; 2020-01-05: Build; 2020-01-12: 2019-01-15
Ergonomics
Last year seat driver survey | bar: 2020-01-05 to 2020-01-12
Analysis ????
| Seat driver survey | 2020-01-05: Seat composites; 2020-01-26: Week of
Suspension
| Shock Dyno Data | 2019-12-29: Shim DR; 2020-01-05: Cut shims
ADAMS Analysis | bar: 2019-12-08 to 2020-02-23
| Test over obstacles | 2019-12-08: Whoops; 2019-12-15: Build Whoops (Justin); 2020-01-05: Ramp DR; 2020-01-12: Ramp Build
Steering
| Slip Angle Data (on old car) | 2019-12-29: Design; 2020-01-12: Build; 2020-01-19: 2019-01-25
ADAMS Oversteer/Min. Turning R | bar: 2019-12-08 to 2020-03-01
| Oversteer Test | 2020-01-05: DAQ Prep
Braking
| Pad friction & tire friction coeff | 2020-01-05: Build
Math model correction | bar: 2020-01-05 to 2020-02-02
| Pressure sensor data from testing | 2020-01-12: DAQ Prep
eCVT
| Engine dyno data | 2020-01-05: old; 2020-01-12: new
Acceleration model w/ controller | bar: 2019-12-08 to 2020-03-01
Stopwatch testing, accel & maneuv. | bar: 2020-01-26 to 2020-03-01
Gearbox
| RPM history data | 2020-01-05: DAQ Logging
AGMA pitting estimation calculation | bar: 2020-01-26 to 2020-03-01
Die penetrant/microscope test | bar: 2020-03-08 to 2020-03-15
Presentation
| Initial Draft / Format | 2020-02-02: 2019-02-01
Gather Resources | bar: 2020-01-26 to 2020-03-22
Poster/Oral Rough Draft | bar: 2020-02-09 to 2020-03-01
Poster/Oral Final Draft | bar: 2020-03-08
Internal Review | bar: 2020-03-15
External Practice | bar: 2020-03-22
Revisions | bar: 2020-03-29
Polish | bar: 2020-04-05
Competitions | bar: 2020-04-12; 2020-05-10; 2020-05-31

## Rough Draft
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33
|  | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 | 2020-04-05 | 2020-04-12 | 2020-04-19 | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17 | 2020-05-24 | 2020-05-31 | 2020-06-07
Subsystem Gameplan | bar: 2019-10-27 to 2019-11-03
Data Collection
Experiment Design | bar: 2019-10-27 to 2019-12-22
Experiment Execution | bar: 2019-11-03 to 2020-02-23
Analysis
Model Building | bar: 2019-10-27 to 2020-03-01
Testing
Test Design | bar: 2019-12-01 to 2019-12-29
Test Preparation | bar: 2020-01-05 to 2020-01-19
| Test Date (Franklin) | 2020-01-05: Track build; 2020-01-26: 2 hours; 2020-02-09: 2 hours; 2020-03-01: 4 hours
Correlation | bar: 2020-01-26 to 2020-03-08
Presentation
| Initial Draft / Format | 2020-02-02: 2019-02-01
Gather Resources | bar: 2020-01-26 to 2020-03-22
| Poster/Oral | 2020-03-01: Rough
Internal Review | bar: 2020-03-15
External Practice | bar: 2020-03-22
Revisions | bar: 2020-03-29
Polish | bar: 2020-04-05
Competition | bar: 2020-04-12; 2020-05-10; 2020-05-31